## Sheet1
Project Order | TBRC Asset | Content Model | Action | Script Status | Size (GB) | Estimated Time to Upload (100GB/day) | Net Time (50% Utilization)
1 | Marc Records | None | Generate Hollis IDs | completed
2 | Methodology | Text (CMID 6.0) | Upload methodology |  | 0.01 | 0.0001 | 0.00015
3 | Instructions | Document (CMID 4.1) | Upload instructions |  | 0.01 | 0.0001 | 0.00015
4 | Copyright | Document (CMID 4.1) | Upload copyright |  | 0.01 | 0.0001 | 0.00015
5 | Image Directorys | PDS (CMID 4.0) | Generate PDS pbjects using Hollis IDs; get back DRS URNs | completed | 2000 | 20 | 30
6 | Archive Directories | Opaque (CMID 1.0) | Generate opaque objects using Hollis IDs; get back DRS URNs |  | 7000 | 70 | 105
7 | Print Masters | Document (CMID 4.1) | Generate document objects using Hollis IDs; get back DRS URNs |  | 600 | 6 | 9
8 | Marc Records | None | Generate Hollis IDs for Unicode Texts
9 | Unicode Texts | Text (CMID 6.0) | Generate text objects using Hollis IDs |  | 5 | 0.05 | 0.075
10 | Electronic Resource ID (TBRC) | None | Obtain Electronic Resource ID
11 | XML Metadata | Text (CMID 6.0) | Generate text objects using Electronic Resource ID |  | 5 | 0.05 | 0.075
12 | Java Codebase | Opaque (CMID 1.0) | Generate opaque objects using Electronic Resource ID |  | 1 | 0.01 | 0.015
[6 empty] | 96.1103 | 144.1654